## Sheet1
ACTIVITY | BEGIN | days to complete
Research on means and tools for project | 2020-06-15 | 4
Gather requirements | 2020-06-19 | 5
Design the sytem | 2020-06-24 | 7
Development of the system | 2020-07-01 | 45
final build and testing | 2020-08-16 | 5
report writing | 2020-06-15 | 68
43997